## Schedule
Week | Start date | Finish date | Sprint | Activity
1 | 2020-04-13 | 2020-04-17 | 1 | Implement the basic UI layout and Tab 1: Add New Entry.
2 | 2020-04-20 | 2020-04-24 | 2 | Implement Tab 2: View Aggregated Analytics.
3 | 2020-04-27 | 2020-05-01 | 3 | Implement Tab 3: View Data History.
4 | 2020-05-04 | 2020-05-08 | 4 | Implement basic Settings layout and Edit Categories tab.
5 | 2020-05-11 | 2020-05-15 | 5 | Implement Manage PIN tab.
6 | 2020-05-18 | 2020-05-22 | 6 | Implement PIN Verification and About tab.
7 | 2020-05-25 | 2020-05-29 |  | Complete backlog by 2020-05-27 and prepare for testing.
8 | 2020-06-01 | 2020-06-05 |  | Perform full test suite along with user tests.
9 | 2020-06-08 | 2020-06-12 |  | Compile collected data and fix bugs.